## Sheet1
PROGRAM EVOLUTION REVIEW TECHNIQUE
Time Unit (in Days)
S/N | NAME | OPTIMISTIC | REALISTIC | PESSIMISTIC | EXPECTED
1 | Project Initiation | 15 | 18 | 22 | 18
2 | Project Planning | 10 | 13 | 18 | 13
3 | Project Execution | 3 | 4 | 7 | 4
4 | Design of Proposed System | 5 | 7 | 10 | 7
| Project Initiation - Completion | 33 | 42 | 57 | 42
| TOTAL |  |  |  | 43